## RACI Matrix
RACI Matrix Template
| Project Leadership |  |  |  |  | Project Team Members |  |  |  |  | Project Sub-Teams |  |  |  |  | External Resources
| Executive Sponsor | Project Sponsor | Steering Committee | Advisory Committee | Role #5 | Project Manager | Tech Lead | Functional Lead | SME | Project Team Member | Developer | Administrative Support | Business Analyst | Role #4 | Role #5 | Consultant | PMO | Role #3 | Role #4 | Role #5
Initiate Phase Activities
- Submit Project Request | A/C | R/A |  |  |  | R/A | A/C | A/C | C
- Request Review by PMO | [5 empty] | R | [10 empty] | A
- Research Solution | I | C |  |  |  | R/A | A/C | A/C | C |  |  |  | C |  |  | C | A/C
- Develop Business Case | I | A/C | I | I |  | R/A | C | C | C |  |  |  | C |  |  | C | C
Plan Phase Activities
- Create Project Charter | C | C |  |  |  | R/A | C | C | C |  |  |  | C |  |  | C
- Create Schedule | I | I | I | I |  | R/A | C | C | C | C | C | C | C |  |  | C | I
- Create Additional Plans as required | I | I | I | I |  | R/A |  |  |  | I | I | I | I |  |  | C | I
Execute Phase Activities
- Build Deliverables | C/I | C/I | C/I | C/I |  |  | R/A | R/A | R/A | R/A | R/A |  |  |  |  | A/C
- Create Status Report | I | I | I | I |  | R/A | R/A | R/A | R/A | [6 empty] | C | I
Control Phase Activities
- Perform Change Management |  | C | C | C |  | R | A | A | A | A | [5 empty] | C | I
Close Phase Activities
- Create Lessons Learned | C | C | C | C |  | R/A | C | C | C | C | C | C | C |  |  | C | C
- Create Project Closure Report | I | I | I | I |  | R/A | I | I | I | I | I | I | I |  |  |  | I
Role
Project Deliverable
(or Activity)

## Instructions
Instructional Notes for the RACI Matrix:
The RACI Matrix is a powerful tool to assist in the identification of roles and assigning of cross-functional responsibilities to a project deliverable or activity. RACI represents: R - Responsibility, A - Accountable, C - Consulted, and I - Informed RACI Definitions: Responsibility = person or role responsible for ensuring that the item is completed Accountable = person or role responsible for actually doing or completing the item Consulted = person or role whose subject matter expertise is required in order to complete the item Informed = person or role that needs to be kept informed of the status of item completion
Simply place an R, A, C, I or any appropriate combination in each of the applicable roles for each activity Each Activity should have at least one individual Accountable while there may be shared responsibilities depending on the activity.