## Punch List
|  | Project Name: | free construction schedule template excel
General Contractor:
Architect:
Owner:
Interested in a punch list software? See how our Closeout app for punch lists works.
Request a demo here.
SCHEDULE
Project Location
Task Number | Task Name | Assigned To | Start Date | End Date | Status | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
[6 empty] | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
1 | Crack in countertop. | Countertops | 2016-03-13 | 2016-03-24 | Open
2 | Door to enter bedroom is uneven. | Doors | 2016-03-13 | 2016-04-04 | Open
3 | Carpet by the back of the clsoet is ripped. | Flooring | 2016-03-14 | 2016-04-04 | Open
4 | Light fixture in the center of the dining room. | Electric | 2016-03-14 | 2016-03-19 | Complete
5 | Crack in tile by main wall. | Flooring | 2016-03-14 | 2016-03-21 | Complete
6 | Corner cabinet status. | Cabinets | 2016-03-14 | 2016-04-04 | Complete
7 | Connection for washing and drying machines. | Plumbing | 2016-03-16 | 2016-03-26 | Open
8 | Scratch in paint by central window. | Painting | 2016-03-16 | 2016-03-18 | Open
9 | Outdoor light. | Electric | 2016-03-17 | 2016-03-18 | Complete
10 | Drywal uneven. | Drywall | 2016-03-17 | 2016-03-19 | Open
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Subcontractor Data
Appliances
Architectural
Brickwork
Concrete
Countertops
Doors
Drywall
Electric
Carpentry
Flooring
Cabinets
Mirrors
Painting
Plumbing
Windows
Gas

## Status Data
Open
Complete
Approved