## Settings
SETTINGS
Project
| Name of the Project | My Project Name
Team
| Project Manager | Joe Preston
| NAME | E-MAIL | PHONE
| Nick | nick@mycompany.com | 000-000-0000
| David | david@mycompany.com | 000-000-0000
| John | john@mycompany.com | 000-000-0000
| Mary | mary@mycompany.com | 000-000-0000
| Caroline | caroline@mycompany.com | 000-000-0000
Insert new row above this line

## Project
Project Planner | [12 empty] | Multiple Project Tracking
HELP
Today's Date | 2019-02-18 | [11 empty] | Project/Task Delay | [8 empty] | Project/Task Duration | [9 empty] | Project/Task Progress | [9 empty] | Project/Task Completed Earlier then Planned
Week Starts from | Monday
Project Start Date | 2014-12-29 | [11 empty] | % Completed (Beyond Projected Duration) | [16 empty] | Project/Task Actual Duration
0
[9 empty] | Dec 2014 |  |  | Jan 2015 | [30 empty] | Feb 2015
Project Name | Project /Task Manager | Project/Task Duration | Project/Task Start Delay | Actual Duration | Complete % | Remaining | time axis 2014-12-29 to 2015-02-19
My Project Name | Joe Preston | 31 | 2 | 36 | 92.57% | 3
Project Task 1 | Nick | 31 | 4 | 34 | 100% | 0 | 36 | 34
Project Task 2 |  | 14 | 6 |  | 70% | 5 | 18 | 14
Project Task 3 |  | 12 | 7 |  | 70% | 4 | 17 | 12
Project Task 4 |  | 12 | 8 |  | 30% | 9 | 18 | 12
Project Task 5 |  | 15 | 2 |  | 20% | 12 | 15 | 15
Project Task 6 |  | 12 | 2 |  | 50% | 6 | 12 | 12
Project Task 7 |  | 14 | 2 |  | 100% | 0 | 14 | 14
Project Task 8 |  | 13 | 2 |  | 100% | 0 | 13 | 13
Project Task 9 |  | 2 | 2 |  | 100% | 0 | 2 | 2
Project Task 10 |  | 8 | 2 |  | 100% | 0 | 8 | 8
Project Task 11 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 12 |  | 28 | 2 |  | 100% | 0 | 28 | 28
Project Task 13 |  | 22 | 2 |  | 100% | 0 | 22 | 22
Project Task 14 |  | 19 | 2 |  | 100% | 0 | 19 | 19
Project Task 15 |  | 16 | 2 |  | 100% | 0 | 16 | 16
Project Task 16 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 17 |  | 19 | 3 |  | 100% | 0 | 20 | 19
Project Task 18 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 19 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 20 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 21 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 22 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 23 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 24 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 25 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 26 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 27 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 28 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 29 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 30 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 31 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 32 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 33 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 34 |  | 11 | 2 |  | 100% | 0 | 11 | 11
Project Task 35 |  | 11 | 2 |  | 100% | 0 | 11 | 11

## HELP
Help
Things to know before you begin
You can use the project planner for planning single projects with multiple tasks. If you rather use something more advanced or perhaps need to plan multiple projects with multiple tasks and sub-tasks, you can download our project manager gantt chart, that is packed with advanced features.
How to begin
Begin from setting up your project name and the team to whom you are planning to assign different tasks of your project, alternatively you can leave these fields blank. All of the fields on the Settings tab are populating corresponding cells and dropdown lists on the Project worksheet.
Planning your first project
Creating your project is very straightforward process. Cells that are highlighted in blue are the cells that you need to modify according to you requirements. Begin by changing the Project start date and Week starts from where you can select any day of the week depending on your specific requirements.
Project Start Date
Week Starts From
Project Row
The row highlighted in grey, which contains your project name, summarizes progress of every task of the project and will display the overall progress of the project and every individual task in it as tasks are created. You do not need to modify anything in this row at all, unless you planning to modify this template and provided that you know what you are doing.
Project Row & Project Progress
Creating project tasks
To create you first task, enter the name of the task as shown on the example, then select the name of the person from the dropdown list that you are planning to assign this task to in the Project/Task Manager column. The dropdown list will be empty is you did not create your team on the Settings tab.
Enter the number of days in the Project/Task Duration column, to create the duration of the task. You can also delay the start day of the task by entering the number of days by which you are planning to delay the start of the task in the Project/Task Start Delay column. This feature can be particularly useful when you need to start your next task after completing the predecessor task.
Sometimes task may take less time or sometimes longer then initially planned, therefore we added column Actual Duration where you can enter the actual number of days that certain tasks did take.
The progress of the task should be entered in the column Complete where you have to enter the percentage of completion of the task which will update the next column labelled Remaining that shows the number of days left until completion as well as progress bars in the tasks progress area.
Inserting / Deleting task rows
To delete the row, click on the row number then right click on the mouse and select Delete from the contextual menu that appears.
Inserting new row is not very difficult, select any task row by clicking on the row number then right click on the mouse and select Copy (Ctrl + C Shortcut) then select the row above which you need to insert your row and right click on the mouse again, but this time click on the Insert Copied Cells (Ctrl + V Shortcut). Just be sure when inserting new rows to always insert them above the last row of the project, this allows for all range formulas to expand and accommodate inserted row correctly.
Copy Row |  | Insert Row

## ©
Terms of Use - EULA
© 2019 Spreadsheet123 LTD. All rights reserved
IMPORTANT—READ CAREFULLY:
This End-User License Agreement (”EULA”) is a legal agreement between you and Spreadsheet123.com that
covers all Microsoft Excel and OpenOffice.org templates or spreadsheets (”TEMPLATES”) and software ("SOFTWARE") made
by Spreadsheet123.com.
By downloading, copying, accessing or otherwise using any TEMPLATES or/and SOFTWARE, you agree to be bound by the
terms of this EULA.
TEMPLATES LICENSE
This TEMPLATE is protected by copyright laws and international copyright treaties, as well as other intellectual
property laws and treaties. Each TEMPLATE is licensed, not sold.
1. GRANT OF LICENSE.
This EULA grants you the right to download this TEMPLATE free of charge for personal use or use within your company
or organization.
You may customize this TEMPLATE with you personal information and use for its intended purpose in personal calculations
documentation or/and communications, but you may not remove or alter any logo, trademark, copyright, hyperlinks,
disclaimers, terms of use or other proprietary notices within this TEMPLATE.
You may not sell, resell, license, rent, lease, lend or otherwise transfer for value without written
permission of SPREADSHEET123.COM
You may not distribute this TEMPLATE in any stand-alone products that contain only the TEMPLATE, or as part of any other
product. You may not copy or post any TEMPLATE on any network computer or broadcast it in any media without
written permission of SPREADSHEET123.COM.
2. RESERVATION OF RIGHTS.
All title and copyrights in and to the Template, and any copies of the Template, are owned by Spreadsheet123.com.
All rights not expressly granted are reserved by Spreadsheet123.com. In particular, this EULA does not grant you any
rights in connection with any trademarks or service marks of Spreadsheet123.com. Use of any Template for any purpose
other than expressly permitted in this EULA is prohibited, and may result in severe civil and criminal penalties.
3. TERMINATION.
Without prejudice to any other rights, Spreadsheet123.com may terminate this EULA if you fail to comply with the
terms and conditions of this EULA. In such event, you must destroy all copies of any TEMPLATE.
4. NOTICE SPECIFIC TO TEMPLATES.
SPREADSHEET123.COM MAKE NO REPRESENTATIONS
ABOUT THE SUITABILITY OF THE TEMPLATES FOR ANY PURPOSE. ALL TEMPLATES ARE PROVIDED
“AS IS” WITHOUT WARRANTY OF ANY KIND. SPREADSHEET123.COM HEREBY DISCLAIM ALL
WARRANTIES AND CONDITIONS WITH REGARD TO THE TEMPLATES, INCLUDING ALL IMPLIED
WARRANTIES AND CONDITIONS OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, TITLE
AND NON-INFRINGEMENT. IN NO EVENT SHALL SPREADSHEET123.COM BE LIABLE FOR ANY SPECIAL,
INDIRECT OR CONSEQUENTIAL DAMAGES OR ANY DAMAGES WHATSOEVER RESULTING FROM LOSS
OF USE, DATA OR PROFITS, WHETHER IN AN ACTION OF CONTRACT, NEGLIGENCE OR OTHER TORTIOUS
ANY REFERENCES TO EVENTS, PEOPLE, PLACES, OR ENTITIES IN THE TEMPLATES IS PURELY FICTITIOUS AND NOT INTENDED TO REPRESENT ANY ACTUAL EVENT,
PERSON, PLACE, OR ENTITY. SPREADSHEET123.COM DISCLAIMS ANY LIKENESS OR SIMILARITIES TO ACTUAL EVENTS, PEOPLE, PLACES, OR ENTITIES, AND
ANY SUCH LIKENESS OR SIMILARITIES ARE UNINTENTIONAL AND PURELY COINCIDENTAL.
5. MISCELLANEOUS.
Some states do not allow the limitation or exclusion of liability for incidental or consequential
damages, so the above limitation may not apply to you.